TravelOS — Pilot Execution Readiness

Operational checklists for a controlled pilot (1–3 agencies). Classifications: Must (pilot blocked without it), Should (high risk if skipped), Post-Pilot (safe to defer). Effort is estimated wall-clock for one engineer + one ops/product owner unless noted.

1. Pilot Environment Checklist

| # | Task | Class | Effort |
| --- | --- | --- | --- |
| 1.1 | Create dedicated pilot Supabase project (separate from dev) | Must | 30 min |
| 1.2 | Create Vercel production deployment pointing at pilot Supabase | Must | 45 min |
| 1.3 | Apply migrations 001–020 via npm run db:push | Must | 30 min |
| 1.4 | Verify migration version in Supabase → Database → Migrations | Must | 15 min |
| 1.5 | Enable Custom Access Token Hook → public.custom_access_token_hook | Must | 15 min |
| 1.6 | Bootstrap first tenant: npm run admin:create with pilot-specific env | Must | 30 min |
| 1.7 | (Optional) Load demo data: npm run db:seed for first demo | Should | 20 min |
| 1.8 | Smoke test: /login → /dashboard → customers/packages/bookings | Must | 45 min |
| 1.8a | Run WP-4B auth QA (scenarios A–F in docs/05-Development/WP-4B-Validation.md) | Must | 2 h |
| 1.9 | Create staging/preview env mirroring pilot (same migrations, separate DB) | Should | 2 h |
| 1.10 | Document pilot URLs, tenant slug, admin contacts in runbook | Should | 30 min |
| 1.11 | Separate pilot vs internal dev Supabase keys in password manager | Must | 15 min |
| 1.12 | Performance spot-check: dashboard load < 5s on pilot URL | Should | 30 min |
| 1.13 | Load test / 50 concurrent users | Post-Pilot | 1–2 days |

Section effort (Must items): ~6–7 h
Section effort (Must + Should): ~10–12 h

2. Production Environment Variables Checklist

Set on Vercel → Project → Settings → Environment Variables (Production). Never commit secrets.

| Variable | Required | Class | Purpose | Effort |
| --- | --- | --- | --- | --- |
| NEXT_PUBLIC_SUPABASE_URL | Yes | Must | Supabase project URL | 5 min |
| NEXT_PUBLIC_SUPABASE_ANON_KEY or NEXT_PUBLIC_SUPABASE_PUBLISHABLE_KEY | Yes | Must | Client auth + RLS | 5 min |
| SUPABASE_SERVICE_ROLE_KEY | Yes | Must | Server-only: invite, onboarding activate, admin scripts | 5 min |
| NEXT_PUBLIC_SITE_URL | Yes | Must | Auth redirect URLs (src/lib/auth/site-url.ts) | 5 min |
| ANTHROPIC_API_KEY | No* | Should | Full LLM for Knowledge/Booking/Support agents | 10 min |
| OPENAI_API_KEY | No | Post-Pilot | Vector embeddings for knowledge upload (fallback if absent) | 10 min |
| ADMIN_EMAIL / ADMIN_PASSWORD / TENANT_SLUG | Script only | Must (bootstrap) | Used by npm run admin:create locally, not Vercel runtime | 5 min |

*Agents work without it (extractive fallback) but pilot AI demos are weak.

| # | Verification task | Class | Effort |
| --- | --- | --- | --- |
| 2.1 | Redeploy after env changes | Must | 10 min |
| 2.2 | Confirm SUPABASE_SERVICE_ROLE_KEY is not prefixed with NEXT_PUBLIC_ | Must | 5 min |
| 2.3 | Hit /api/health/supabase → ok: true | Must | 5 min |
| 2.4 | Document env ownership and rotation date | Should | 30 min |
| 2.5 | Per-tenant env isolation (N/A — single app, multi-tenant DB) | N/A | — |

Section effort: ~1 h

3. Supabase Configuration Checklist

| # | Task | Class | Effort |
| --- | --- | --- | --- |
| 3.1 | Database: All migrations applied through 020_auth_active_status_rls.sql | Must | 30 min |
| 3.2 | Auth → Hooks: Custom Access Token → public.custom_access_token_hook | Must | 10 min |
| 3.3 | Auth → URL Configuration: Site URL = pilot app origin | Must | 10 min |
| 3.4 | Redirect URLs allowlist: /auth/callback, /reset-password, /onboarding (+ wildcard if used) | Must | 15 min |
| 3.5 | Auth → Providers: Email enabled; signup disabled (invite-only) | Must | 5 min |
| 3.6 | Auth → Email templates: Reset password + Invite user branded (TravelOS) | Should | 1 h |
| 3.7 | RLS: Confirm enabled on tenant tables (migrations handle this) | Must | 15 min |
| 3.8 | Storage: knowledge-documents bucket exists (migration 016) | Should (if AI demo) | 15 min |
| 3.9 | Extensions: vector enabled for knowledge RAG (013) | Should (if AI demo) | 15 min |
| 3.10 | Backups: Confirm daily backups on; note Pro PITR if needed | Should | 15 min |
| 3.11 | Auth logs: Spot-check failed login / invite events during QA | Should | 20 min |
| 3.12 | Database advisors / security linter in Supabase Dashboard | Post-Pilot | 1 h |
| 3.13 | Read replicas / connection pooling tuning | Post-Pilot | 2–4 h |

Reference: docs/05-Development/AuthEmailSetup.md, docs/05-Development/Deployment.md

Section effort (Must): ~1.5 h
Section effort (Must + Should for AI): ~3.5 h

4. SMTP Configuration Checklist

| # | Task | Class | Effort |
| --- | --- | --- | --- |
| 4.1 | Configure SMTP in Supabase (SendGrid / SES / Resend) | Must | 1–2 h |
| 4.2 | Set sender domain (SPF, DKIM, DMARC) | Must | 1–4 h* |
| 4.3 | Send test invite email → complete onboarding flow | Must | 30 min |
| 4.4 | Send test reset email → complete reset flow | Must | 30 min |
| 4.5 | Customize Invite user template (link → /auth/callback?next=/onboarding) | Should | 30 min |
| 4.6 | Customize Reset password template | Should | 30 min |
| 4.7 | Verify emails not landing in spam (pilot inboxes) | Should | 30 min |
| 4.8 | Document fallback: admin copies onboarding link from invite UI if email fails | Should | 15 min |
| 4.9 | Dedicated transactional subdomain (e.g. auth.agency.com) | Post-Pilot | 2 h |
| 4.10 | Bounce/complaint monitoring | Post-Pilot | 2 h |

*DNS propagation may extend calendar time.

Without SMTP: Invite and forgot-password cannot complete self-service in production (manual link copy only).

Section effort (Must): ~3–5 h (depends on DNS)

5. Vercel Deployment Checklist

| # | Task | Class | Effort |
| --- | --- | --- | --- |
| 5.1 | Import GitHub repo; connect production branch (main) | Must | 20 min |
| 5.2 | Set all Must env vars (Section 2) for Production | Must | 15 min |
| 5.3 | Confirm Node 20 (matches CI) | Must | 5 min |
| 5.4 | First deploy succeeds; CI green (lint, typecheck, build) | Must | 30 min |
| 5.5 | Custom domain + HTTPS (agency pilot subdomain) | Should | 1–2 h |
| 5.6 | Set NEXT_PUBLIC_SITE_URL to custom domain (not *.vercel.app) before auth QA | Must (if custom domain) | 10 min |
| 5.7 | Disable or protect preview deployments from production Supabase | Should | 30 min |
| 5.8 | Enable Vercel Analytics (basic Web Vitals) | Should | 15 min |
| 5.9 | Configure deployment protection on main (require PR + CI) | Should | 30 min |
| 5.10 | Document rollback: Vercel → Deployments → Promote previous | Must | 15 min |
| 5.11 | Sentry / error tracking | Post-Pilot | 2–4 h |
| 5.12 | Edge config / geo routing | Post-Pilot | — |

Section effort (Must): ~1.5 h
Section effort (Must + Should + domain): ~4–5 h

6. Tenant Onboarding Checklist

Per first pilot agency (repeat for each tenant until multi-tenant provisioning is automated).

| # | Task | Class | Effort |
| --- | --- | --- | --- |
| 6.1 | Agree tenant name, slug, timezone, currency (future settings) | Must | 30 min (meeting) |
| 6.2 | Run admin:create or manual provision_tenant.sql for tenant admin | Must | 30 min |
| 6.3 | Confirm admin users.status = active, role tenant_admin | Must | 10 min |
| 6.4 | Admin logs in at pilot URL; lands on dashboard | Must | 10 min |
| 6.5 | Admin invites sales + finance users; verify email/onboarding | Must | 45 min |
| 6.6 | Verify pending user blocked until onboarding completes (WP-4A) | Must | 20 min |
| 6.7 | Create destinations (or use seeded geography) | Must | 30 min |
| 6.8 | Create 1–2 real packages (published) or use seed | Must | 1 h |
| 6.9 | Upload knowledge documents (Settings → Knowledge) if AI in scope | Should | 45 min |
| 6.10 | Walk through forgot password for one user | Should | 15 min |
| 6.11 | Hand off role guide (Admin / Sales / Finance permissions) | Should | 30 min |
| 6.12 | Decide: seed data vs clean tenant (recommend clean for real pilot) | Must (decision) | 15 min |
| 6.13 | Super Admin cross-tenant console | Post-Pilot | — |
| 6.14 | Self-service tenant signup | Post-Pilot | — |

Section effort per agency (Must): ~4 h
Section effort per agency (Must + Should): ~6–7 h

7. First Agency Demo Script

Duration: ~20 minutes (core ops) + 5 min optional AI
Audience: Agency owner + sales lead + finance
Prerequisites: Section 1 complete; tenant onboarded (Section 6) or seed loaded

Pre-demo (15 min before)

| Step | Action |
| --- | --- |
| P1 | Open pilot URL in incognito; login as tenant admin |
| P2 | Confirm dashboard shows data (seed or real) |
| P3 | Open second browser: sales_agent login ready |
| P4 | If AI demo: confirm ANTHROPIC_API_KEY set; test one Knowledge question |

Script

| Time | Module | Action | Proof point |
| --- | --- | --- | --- |
| 0:00 | Intro | Landing /home → Sign in | EN/AR, professional SaaS |
| 2:00 | Dashboard | Status cards, revenue, recent bookings | Real-time ops visibility |
| 4:00 | Customers | Search/create individual; show corporate | CRM foundation |
| 6:00 | Packages | Open published package; itinerary + pricing tiers | Catalog ready to sell |
| 9:00 | Bookings | Open draft → Confirm; show travelers & history | Controlled lifecycle |
| 12:00 | Payments | Record partial payment; show status update | Finance integration |
| 14:00 | Security | Mention tenant isolation, roles, deactivate user | Enterprise trust |
| 15:00 | Users | Show invite → pending → (reference onboarding email) | Team scaling |
| 17:00 | Knowledge (optional) | Ask cancellation policy; show citations | AI over their docs |
| 19:00 | Booking Agent (optional) | Search packages → draft only; staff confirms | Human-in-the-loop |
| 20:00 | Close | Pilot next steps, support channel, feedback form | — |

Do not demo in first meeting unless stable: Support ticket queue UI, Invoices deep dive, package cover upload.

Class: Running this script once internally = Must (2 h prep + 1 h dry run). Customizing for agency = Should.

8. Go-Live Checklist

Go-live = pilot agency using production URL for real (or semi-real) operations.

| # | Gate | Class | Effort |
| --- | --- | --- | --- |
| 8.1 | All Must items in Sections 1–6 complete | Must | — |
| 8.2 | WP-4B scenarios A, D, E, F passed on pilot URL | Must | 2 h |
| 8.3 | SMTP invite + reset received by real agency inboxes | Must | 30 min |
| 8.4 | Agency admin + ≥1 sales + ≥1 finance user active | Must | — |
| 8.5 | ≥1 published package; ≥1 booking created by agency (not seed) | Should | 1 h supervised |
| 8.6 | Support channel defined (email/Slack); escalation owner named | Must | 30 min |
| 8.7 | Pilot agreement / DPA / data location acknowledged | Should | Legal |
| 8.8 | Backup restore tested | Post-Pilot | 2 h |
| 8.9 | Incident response runbook shared with team | Should | 1 h |
| 8.10 | Go/No-Go meeting sign-off (Product + Ops + Security) | Must | 1 h meeting |

Pilot go-live decision: Conditional GO when 8.1–8.4 and 8.6 pass.

Section effort: ~5–6 h (excluding legal)

9. Rollback Plan

Application rollback (Vercel)

| Step | Action | Effort |
| --- | --- | --- |
| R1 | Identify last known-good deployment in Vercel → Deployments | 5 min |
| R2 | Promote to Production (or revert Git commit on main and redeploy) | 15 min |
| R3 | Verify /login, /dashboard, one CRUD path | 15 min |
| R4 | Communicate to pilot agency: brief maintenance window | 10 min |

Class: Document R1–R4 = Must before go-live. Effort if needed: ~45 min

Database rollback

| Scenario | Action | Class | Effort |
| --- | --- | --- | --- |
| Bad app deploy, schema unchanged | Vercel rollback only | Must | 45 min |
| Bad migration applied | Do not force-push; restore Supabase backup / PITR (Pro) | Must (plan) | 1–4 h |
| Data corruption (seed mistake) | Re-run targeted cleanup or restore backup; db:seed only on demo tenants | Should | 1–2 h |
| Auth hook misconfiguration | Disable hook temporarily; fix JWT claims; re-enable | Should | 30 min |

Auth / user rollback

| Scenario | Action |
| --- | --- |
| Mass bad invites | Deactivate users in Users UI; revoke via existing session-revoke path |
| Wrong tenant admin | Deactivate; re-run admin:create with new email (new tenant slug if needed) |

Rollback decision matrix

| Trigger | Roll back app? | Roll back DB? |
| --- | --- | --- |
| UI bug, no schema change | Yes | No |
| RLS too permissive | Yes + hotfix | Maybe (if data leaked — incident) |
| Failed migration mid-apply | No new deploy | Yes — restore |
| SMTP broken | No | No — fix SMTP; use manual onboarding links |

Class: Rollback plan documented = Must; full restore drill = Post-Pilot.

10. Risk Register

| ID | Risk | Likelihood | Impact | Mitigation | Class |
| --- | --- | --- | --- | --- | --- |
| R01 | Migrations not fully applied (docs say 010, repo at 020) | Med | High | Verify migration list in Dashboard; use db:push | Must |
| R02 | SMTP misconfigured — invites/resets fail | Med | High | Section 4 tests; manual onboarding link fallback | Must |
| R03 | Custom access token hook off in cloud | Med | High | Dashboard check; login without tenant_id in JWT fails ops | Must |
| R04 | NEXT_PUBLIC_SITE_URL wrong → broken auth links | Med | High | Match Supabase Site URL exactly | Must |
| R05 | Service role key exposed in client bundle | Low | Critical | Never NEXT_PUBLIC_ prefix; audit Vercel env | Must |
| R06 | Pending user accesses data before onboarding | Low | Critical | WP-4A QA scenario D5 | Must |
| R07 | AI demos fail without ANTHROPIC_API_KEY | High | Med | Set key or skip AI in first demo | Should |
| R08 | Pilot uses seed data in production DB | Med | Med | Use clean tenant for real pilot | Should |
| R09 | No automated E2E — regression undetected | Med | Med | Manual DemoScript + WP-4B before go-live | Should |
| R10 | Invoices module confuses finance users | Med | Low | Brief scope: payments primary | Should |
| R11 | JWT stale after role change | Low | Med | Document “log out and back in”; revoke on deactivate | Should |
| R12 | Supabase free tier limits (auth emails, DB size) | Med | Med | Monitor usage; upgrade plan if needed | Post-Pilot |
| R13 | No Sentry — errors invisible | Med | Med | Support channel + Supabase/Vercel logs | Post-Pilot |
| R14 | Single-region outage | Low | High | Communicate SLA; Supabase status page | Post-Pilot |
| R15 | Agency expects package cover images | Med | Low | Set expectation: roadmap item | Post-Pilot |

Summary: classification & effort

Must complete before pilot

| Area | Est. effort |
| --- | --- |
| Pilot environment (1) | 6–7 h |
| Production env vars (2) | 1 h |
| Supabase config (3) | 1.5 h |
| SMTP (4) | 3–5 h |
| Vercel deploy (5) | 1.5 h |
| First tenant onboarding (6) | 4 h |
| Internal demo dry run (7) | 3 h |
| Go-live gates (8) — technical | 3 h |
| Rollback plan documented (9) | 1 h |
| Total (parallelizable) | ~18–22 h (~3 engineer-days) |

Should complete before pilot

| Area | Est. effort |
| --- | --- |
| Staging env, custom domain, branded emails | 4–6 h |
| AI keys + knowledge upload | 2 h |
| Full WP-4B + DemoScript dry run | 2 h |
| Support/incident runbook | 1.5 h |
| Per-agency onboarding (Should items) | +2 h/agency |
| Additional | ~10–12 h |

Can wait until post-pilot

- E2E / Playwright suite

- Sentry / APM

- Backup restore drill

- Super Admin console

- Package cover upload

- Payment/booking advanced filters

- Load testing

- Dedicated auth email subdomain + bounce monitoring

- Tenant self-service settings UI

Post-pilot backlog: ~2–4 weeks engineering (not blocking pilot).

Go / No-Go (pilot execution)

| Criterion | Status |
| --- | --- |
| Technical Must checklist complete | Required |
| SMTP + auth flows verified on pilot URL | Required |
| One agency onboarded with active users | Required |
| Rollback plan acknowledged | Required |
| Recommendation | Proceed to pilot when Must total ~18–22 h is done and R01–R06 mitigations verified |

This is an execution playbook only — no code changes. For a single printable runbook, combine Sections 1, 2, 3, 4, 5, and 8 into one “Pilot Day 1” checklist.