TravelOS MVP Gap Analysis & Completion Plan

Date: 2026-06-02
Goal: Complete MVP using the existing foundation.
Constraints: No new AI agents, no orchestration, no new languages, no DB schema changes unless unavoidable.

Executive Summary

TravelOS has a production-grade platform shell (auth, tenancy, RLS, i18n, landing, three AI agents) but core commercial workflows are incomplete. UI pages exist for Customers, Packages, Bookings, and Payments, yet nested resources (contacts, itinerary, pricing, travelers, line items) are largely missing. The Booking Agent has solid HITL infrastructure but fails most conversational acceptance criteria.

Estimated overall MVP completion: ~55–60% against documented acceptance criteria.

| Priority (your order) | Completion | Blocks MVP exit? |
| --- | --- | --- |
| 1. Booking Agent | ~60% | Yes — Phase 5 exit criterion |
| 2. Customers | ~35% | Yes — CRM + booking dependency |
| 3. Packages | ~30% | Critical — pricing/itinerary blocks bookings |
| 4. Dashboard KPIs | ~50% UI / ~30% spec | Medium |
| 5. Seed Data | ~25% | High — empty tenant = no demo |
| 6. E2E Testing | ~0% | Medium — launch confidence |

Key insight: Your priority list is correct for focus, but Packages must be executed before Booking Agent and E2E can succeed. Bookings also needs travelers + line items (implicit dependency, ~2–3 days) — not in your list but required for the commercial loop.

Part 1 — MVP Gap Analysis

Foundation (Confirmed Complete)

| Area | Status |
| --- | --- |
| Supabase + migrations (001–017) | Done |
| Auth, JWT claims, middleware | Done |
| Multi-tenancy + RLS | Done |
| Landing page (/, /home) | Done |
| i18n (AR/EN, cookie, RTL/LTR) | Done |
| Knowledge Agent (Claude + RAG) | Done |
| Support Agent + Ticketing | Done |
| Knowledge Base admin | Done |

Architecture pattern in use: Refine data provider → Supabase JS (direct), not REST /api/* for core modules. Only AI, knowledge, and health routes exist under src/app/api/.

Priority 1 — Booking Agent MVP

Current status (~60%)

Implemented:

| Layer | Detail |
| --- | --- |
| API | POST /api/ai/booking-agent — auth, tenant, ai.booking.use RBAC, Zod |
| Orchestrator | Rule-based (booking-agent.ts, booking-intent.ts) — not LLM |
| Tools | Package search, customer search, booking lookup, draft create/update, cancellation note |
| HITL | confirm_action → apply_action; draft-only writes; never auto-confirms |
| UI | /ai/booking — chat + Draft Builder sidebar, package cards, confirm button |
| i18n | EN/AR reply templates |
| Persistence | ai_sessions, ai_conversations, ai_messages, ai_logs |
| Nav/RBAC | Refine resource ai-booking; finance_officer denied |

Acceptance criteria:

| Story | Verdict | Notes |
| --- | --- | --- |
| US-AI-BKG-001 Create draft from chat | Fail | create_draft intent returns help text only; draft via sidebar form |
| US-AI-BKG-002 Update from chat | Fail | Backend supports update; no UI or chat-driven path |
| US-AI-BKG-003 Status lookup | Pass | Reference lookup works |
| US-AI-BKG-004 Suggest packages | Partial | Filtered list; no ranking or rationale |
| US-AI-BKG-005 Collect travelers | Partial | Single traveler in form; no chat parsing, no DOB |

Missing pieces

- Chat → draft pipeline — Parse customer/package/date/pax from NL (EN/AR) → build confirm_action payload

- Update-draft UX — Chat path + UI to load existing draft by reference and apply changes

- Multi-traveler support — Multiple tiers (adult/child/infant) in tools and form

- Package card → draft prefill — One-click from recommendation to Draft Builder

- Simple ranking — Sort by destination match, price, duration; template rationale strings

- get_package_detail tool — Listed in workflow docs; not implemented

- Conversation context — Prior messages stored but not loaded for multi-turn state

- Integration tests — Tenant isolation, draft-only guard, no auto-confirm

- Doc sync — Phase5-Agent-Handoff.md still says "stub"; API.md missing booking-agent contract

Out of scope (per constraints): LLM orchestration, multi-agent router, MCP layer, new DB tables.

Implementation plan

| Step | Work | Output |
| --- | --- | --- |
| 1 | Extend booking-intent.ts entity extraction (customer name, package title, pax counts, ref) | Structured intent payload from chat |
| 2 | Add buildConfirmActionFromIntent() in orchestrator | Chat → confirm_action without LLM |
| 3 | Wire create_draft / update_draft intents to preview flow | US-AI-BKG-001/002 pass |
| 4 | UI: update mode (enter ref → load draft → edit travelers/items) | Human can complete update path |
| 5 | Multi-traveler rows in Draft Builder + tool support | US-AI-BKG-005 partial |
| 6 | Package ranking (rule-based score) + card prefill | US-AI-BKG-004 partial |
| 7 | Tests + doc updates | CI confidence, no drift |

Effort estimate: 4–6 dev-days

Priority 2 — Customers Module

Current status (~35%)

Implemented:

- List / create / show / edit pages (src/app/customers/)

- Core fields: type, names, email, phone

- Zod validation (customer-form.ts)

- DB tables: customers, customer_contacts, customer_addresses + RLS

- RBAC in access-control provider

Acceptance criteria:

| Story | Status |
| --- | --- |
| US-CUST-001 Create | Partial — form requires last_name only for individuals vs spec both names |
| US-CUST-002 Contacts | Not done |
| US-CUST-003 Addresses | Not done |
| US-CUST-004 Search | Not done — no search/filter on list |
| US-CUST-005 Edit | Done (core fields) |
| US-CUST-006 Soft delete | Not done — useDelete hard-deletes; lists don't filter deleted_at |
| US-CUST-007 Booking history | Not done |
| US-CUST-008 Duplicate detection | Partial — DB unique index only; no UX on 409 |

Missing pieces

- Contacts CRUD nested on show page

- Addresses CRUD nested on show page

- List search (name/email/phone) + type filter + pagination

- Soft delete via deleted_at update + permanent list filter

- Booking history section on show (join bookings by customer_id)

- Duplicate email warning on create (catch unique violation)

- notes field in form/show (column exists)

- RBAC-gated delete (CanAccess — sales_agent lacks customers.delete)

- Validation alignment with spec (both names for individuals)

Implementation plan

| Step | Work | Output |
| --- | --- | --- |
| 1 | CustomerContactsSection + CustomerAddressesSection on show | US-CUST-002/003 |
| 2 | Search input + filters on list page | US-CUST-004 |
| 3 | Replace delete with soft-delete mutation; filter lists | US-CUST-006 |
| 4 | Bookings tab/section on show | US-CUST-007 |
| 5 | Duplicate email handler on create | US-CUST-008 |
| 6 | RBAC gates + notes field | Polish |

Effort estimate: 3–4 dev-days

Priority 3 — Packages Module

Current status (~30%)

Implemented:

- List / create / show / edit — title, description, destination, duration

- Publish/archive via status toggle on list (no validation)

- DB: package_days, package_day_activities, package_pricing, package_media + RLS

- Bookings create filters status = published

- Booking Agent reads package_pricing in tools

Acceptance criteria:

| Story | Status |
| --- | --- |
| US-PKG-001 Create | Done |
| US-PKG-002 Itinerary | Not done — DB ready, zero UI |
| US-PKG-003 Pricing tiers | Not done — DB ready, zero UI |
| US-PKG-004 Save as draft | Done |
| US-PKG-005 Publish | Partial — status flip only |
| US-PKG-006 Archive | Partial |
| US-PKG-007 Search/filter | Not done |
| US-PKG-008 Cover image | Not done — defer POST-MVP |

Missing pieces

- Itinerary editor — CRUD on package_days + package_day_activities (ordered)

- Pricing tier editor — CRUD on package_pricing (adult/child/infant amounts)

- Publish gate — Block publish unless ≥1 itinerary day AND ≥1 price tier

- Enriched show page — Itinerary timeline + pricing table + publish/archive actions

- List filters — destination, status

- Zod validation — title max length, positive duration_days

- Soft delete + list filter (same pattern as customers)

This is the highest structural blocker — without pricing, bookings cannot auto-calculate, Booking Agent drafts have $0 totals, and E2E flow #3 fails.

Implementation plan

| Step | Work | Output |
| --- | --- | --- |
| 1 | PackageItineraryEditor on show/edit | US-PKG-002 |
| 2 | PackagePricingEditor on show/edit | US-PKG-003 |
| 3 | Publish validation (client-side check before status update) | US-PKG-005 |
| 4 | Enriched show page layout | Complete package detail |
| 5 | List filters + Zod | US-PKG-007 |
| 6 | Soft delete pattern | Consistency |

Effort estimate: 4–5 dev-days

Priority 4 — Dashboard KPIs

Current status (~50% UI / ~30% spec)

Implemented:

- Dashboard page with 4 status count cards, revenue, outstanding, recent bookings table

- i18n (AR/EN)

- Client-side aggregation via Refine useList (pageSize 100 — inaccurate at scale)

Acceptance criteria:

| Story | Status |
| --- | --- |
| US-DASH-001 Booking counts | Partial — UI yes, capped, no API |
| US-DASH-002 Revenue + outstanding | Partial — shown to all roles |
| US-DASH-003 Sales agent own bookings | Not done — no created_by filter |

Missing pieces

- Server-side aggregation (route or Supabase RPC) — remove 100-record cap

- RBAC: hide financial cards from sales_agent (dashboard.financial permission exists in frontend only)

- Sales agent: filter recent bookings by created_by = auth.uid()

- Seed dashboard.* permissions in 008_seed_reference.sql (frontend has them; DB doesn't)

- Optional: GET /api/dashboard/stats per API.md spec

Implementation plan

| Step | Work | Output |
| --- | --- | --- |
| 1 | Create src/app/api/dashboard/stats/route.ts with aggregated SQL | Accurate KPIs |
| 2 | Refactor dashboard page to fetch from API | Single request |
| 3 | CanAccess / role check for financial cards | US-DASH-002 RBAC |
| 4 | Sales-agent scoping on recent bookings | US-DASH-003 |
| 5 | Add dashboard permissions to reference seed | DB alignment |

Effort estimate: 1.5–2 dev-days

Priority 5 — Seed Data

Current status (~25%)

Implemented:

| Asset | Contents |
| --- | --- |
| 008_seed_reference.sql | 4 roles, module CRUD permissions |
| 010_seed_geography.sql | 20 countries, ~38 cities |
| 015_rls_ai.sql | AI/knowledge permissions |
| provision_tenant.sql | Manual tenant + admin user |
| create-admin-user.mjs | Script-based bootstrap |

Missing:

| Gap | Impact |
| --- | --- |
| Demo business data (destinations, customers, packages, bookings, payments) | Empty dashboard; agent has nothing to search |
| Idempotent seed script | No one-command demo setup |
| npm run db:seed | No developer workflow |
| Supabase [db.seed] config | No CLI seed |
| Tenant-scoped destinations seed | Packages need destinations |
| Dashboard permissions in DB seed | RBAC mismatch |

Implementation plan

| Step | Work | Output |
| --- | --- | --- |
| 1 | database/seed/demo_business.sql — idempotent, tenant-scoped | Realistic demo tenant |
| 2 | Seed: 3 destinations, 5 customers (with 1 contact each), 3 published packages (itinerary + pricing), 5 bookings (mixed status), 3 payments | Full commercial loop |
| 3 | npm run db:seed script wrapping SQL + docs | Developer UX |
| 4 | Document in Deployment.md | Onboarding path |
| 5 | Tie to demo tenant from provision_tenant.sql or standalone UUIDs | Deterministic E2E |

Suggested demo data shape:

- 3 destinations (Istanbul, Dubai, Cairo)

- 5 customers (2 individual, 2 corporate, 1 with duplicate-risk email for testing)

- 3 packages: 2 published (full itinerary + 3-tier pricing), 1 draft

- 5 bookings: 2 draft, 2 confirmed, 1 cancelled

- 3 payments linked to confirmed bookings

Effort estimate: 2–3 dev-days

Priority 6 — End-to-End Testing

Current status (~0%)

Documented in docs/05-Development/Testing.md:

- Playwright E2E, five critical flows

- CI should run tests on merge to main

Actual:

- No @playwright/test, no e2e/ folder, no test scripts in package.json

- CI (.github/workflows/ci.yml) runs lint + typecheck + build only

- TASKS.md lists E2E as post-MVP backlog

Missing pieces

- Playwright install + playwright.config.ts

- Auth fixture (login helper, storageState)

- Seeded test tenant dependency (WP-F)

- Smoke test: login → dashboard loads

- Business test: create customer → create/publish package → create booking → confirm → record payment

- CI job (main branch or nightly)

- .gitignore for Playwright artifacts

Implementation plan

| Step | Work | Output |
| --- | --- | --- |
| 1 | Playwright setup + config (webServer: next dev) | Tooling |
| 2 | e2e/helpers/auth.ts — login as sales_agent / tenant_admin | Reusable fixture |
| 3 | e2e/smoke.spec.ts — login → dashboard | CI gate |
| 4 | e2e/commercial-loop.spec.ts — full booking journey | MVP confidence |
| 5 | CI job with seeded Supabase env | Automated regression |
| 6 | package.json scripts: test:e2e, test:e2e:ui | Developer UX |

Effort estimate: 3–4 dev-days

Implicit Dependency — Bookings Module (~60%, not in your list)

Bookings pages exist but the create form is minimal — customer + package + date only. No travelers, line items, or auto-total.

| Gap | Acceptance impact |
| --- | --- |
| No travelers on create/edit | US-BKG-002 fail |
| No line items from pricing | US-BKG-003/004 fail |
| total_amount stays 0 | Payments/outstanding meaningless |
| No search on list | US-BKG-009 fail |

Effort: 2–3 dev-days — must run after Packages pricing, before Booking Agent polish and E2E.

Part 2 — MVP Completion Plan

Guiding principles

- Unblock the commercial loop first — Packages → Bookings → then Booking Agent

- No orchestration — extend rule-based agent with better entity extraction + HITL

- No new REST layer for Customers/Packages unless dashboard/E2E require it — keep Refine + Supabase

- No DB schema changes — all tables exist; work is UI + seed + API route for dashboard

- Seed early in parallel — accelerates agent dev and E2E

Work packages

| ID | Name | Scope | Days |
| --- | --- | --- | --- |
| WP-A | Packages completion | Itinerary, pricing, publish gate, filters | 4–5 |
| WP-B | Bookings enrichment | Travelers, line items, auto-total | 2–3 |
| WP-C | Customers completion | Contacts, addresses, search, soft delete, history | 3–4 |
| WP-D | Booking Agent MVP | Chat→draft, update UX, multi-traveler, ranking | 4–6 |
| WP-E | Dashboard KPIs | Server stats, RBAC gating, scoping | 1.5–2 |
| WP-F | Seed data | Demo tenant business data + script | 2–3 |
| WP-G | E2E testing | Playwright smoke + commercial loop + CI | 3–4 |

Total: ~20–27 dev-days (~4–5.5 calendar weeks, one developer)

Part 3 — Implementation Roadmap

Recommended execution order

Your stated priority is respected for focus and review order, but execution should follow dependencies:

Sprint 1 — Unblock commercial loopSprint 2 — CRM + AgentSprint 3 — Polish + QualityWP-A PackagesWP-B BookingsWP-F Seed skeletonWP-C CustomersWP-D Booking AgentWP-F Seed finalizeWP-E DashboardWP-G E2E Testing

Sprint schedule

| Sprint | Duration | Focus | Deliverables |
| --- | --- | --- | --- |
| S1 | Week 1 | Packages + Bookings + Seed start | Publishable packages with pricing; bookings with travelers/items/totals; seed script skeleton |
| S2 | Week 2 | Customers + Booking Agent + Seed | Full CRM; chat-driven drafts; demo data complete |
| S3 | Week 3 | Dashboard + E2E | RBAC KPIs; Playwright smoke + commercial loop in CI |

Priority vs execution slot

| Your priority | Recommended sprint | Rationale |
| --- | --- | --- |
| 1. Booking Agent | S2 | Needs published packages with pricing + working booking pipeline |
| 2. Customers | S2 (parallel with agent) | Independent; needed for realistic demos |
| 3. Packages | S1 first | Highest blocker — move ahead of stated order |
| 4. Dashboard | S3 | Meaningful only with seed data |
| 5. Seed Data | S1 parallel → S2 finalize | Unblocks agent testing and E2E |
| 6. E2E | S3 last | Requires stable flows + seed |

MVP exit checklist

When all work packages close, these must pass:

- Sales agent publishes package (itinerary + pricing validated)

- Sales agent creates customer with contacts/addresses

- Sales agent creates booking with travelers + auto-calculated total

- Sales agent confirms booking and records payment

- Dashboard shows correct counts (financial cards role-gated)

- Booking Agent creates draft from chat; human confirms in Bookings UI

- Booking Agent returns status by reference

- Demo tenant seed loads in one command

- Playwright smoke + commercial loop pass

- No new AI agents, orchestration, languages, or schema changes

Risks & mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Packages delay cascades | Blocks agent, bookings, E2E | Start S1 with Packages; defer cover image |
| Chat agent without LLM feels brittle | US-AI-BKG-001/002 edge cases | Clarifying questions + HITL preview (already designed) |
| Refine nested CRUD verbose | Slows Customers/Packages | Inline sub-forms on show pages, not separate routes |
| E2E flaky with Supabase auth | CI noise | Dedicated test tenant + storageState fixture |
| Doc drift continues | Wrong priorities | Update handoff/API/TASKS as each WP closes |
| 100-record dashboard cap | Wrong KPIs at scale | Fix in WP-E before demo |

POST-MVP deferrals

- REST API layer for core modules

- Cover image upload (US-PKG-008)

- LLM-driven booking agent

- Full 5-flow E2E + RLS security SQL suite

- Invoice PDF, Stripe, email notifications

- Analytics/product KPIs (PRD §8)

- Spanish/Portuguese/French/German i18n

Summary

TravelOS is ~55–60% MVP-complete. The platform foundation is solid; the gap is depth in commercial modules and closing the booking loop. Packages (pricing + itinerary) is the critical path item — it should run in Sprint 1 even though it is priority #3 in your list. Booking Agent polish follows naturally once packages and bookings work end-to-end.

Recommended first action: WP-A (Packages completion) + WP-F skeleton (seed script structure) in parallel.

No code generated — ready to implement when you specify which work package to start.